## Summary
StockFlow Test Execution Summary
Project | StockFlow | Status | Count | Module | Total | Severity | Open/Fixed Defects | Notes
Execution Cycle | Cycle 1 | Pass | 109 | Authentication | 14 | Critical | 0 | No critical defect expected
Prepared By | Nguyen Phuc Tan | Fail | 12 | Dashboard | 10 | High | 5 | Important business rule defects
Execution Start Date | 2026-06-23 | Blocked | 3 | Product Management | 30 | Medium | 5 | Functional/UI defects
Execution End Date | 2026-06-28 | Not Run | 5 | Stock-In | 14 | Low | 2 | Minor UI/text defects
Environment | Local - Chrome, Spring Boot, MySQL | Total | 129 | Stock-Out | 16 | Total | 12 | Total logged defects
Total Test Cases | 129 |  |  | Transaction History | 10
Pass Rate | 84.5% |  |  | Inventory Report | 10
|  |  |  | Role-Based Access | 13
|  |  |  | UI and Validation | 12
Final Conclusion | Conditional Pass
Recommendation | Fix failed cases, retest related defects, and run regression for affected modules.
Major Findings | Most core flows pass. Failed cases are documented in Defect Summary.
Next Action | Retest failed cases and update execution status.
Document Status | Draft

## Test Execution
Test Case ID | Module | Test Case Title | Priority | Test Type | Expected Result | Test Data | Execution Date | Tester | Actual Result | Status | Bug ID | Retest Status | Notes
TC-AUTH-001 | Authentication | Verify login page loads successfully | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-AUTH-002 | Authentication | Verify Admin login with valid credentials | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-AUTH-003 | Authentication | Verify Staff login with valid credentials | High | Role-Based Access | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-AUTH-004 | Authentication | Verify login with invalid username | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-AUTH-005 | Authentication | Verify login with invalid password | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-AUTH-006 | Authentication | Verify username required validation | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-AUTH-007 | Authentication | Verify password required validation | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result does not match expected result | Fail | BUG-001 | Pending | Defect logged for investigation
TC-AUTH-008 | Authentication | Verify both fields required validation | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-AUTH-009 | Authentication | Verify logout redirects to login page | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-AUTH-010 | Authentication | Verify protected page requires login | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-AUTH-011 | Authentication | Verify expired/invalid token redirects to login | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-AUTH-012 | Authentication | Verify login error message is clear | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-AUTH-013 | Authentication | Verify login form clears password after failed login | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-AUTH-014 | Authentication | Verify role is stored after successful login | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-DASH-001 | Dashboard | Verify dashboard loads after login | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-DASH-002 | Dashboard | Verify total products count | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-DASH-003 | Dashboard | Verify active products count | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-DASH-004 | Dashboard | Verify inactive products count | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-DASH-005 | Dashboard | Verify total stock quantity | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-DASH-006 | Dashboard | Verify low stock product count | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result does not match expected result | Fail | BUG-002 | Pending | Defect logged for investigation
TC-DASH-007 | Dashboard | Verify out of stock product count | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-DASH-008 | Dashboard | Verify dashboard refresh button | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-DASH-009 | Dashboard | Verify dashboard handles API error | Medium | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result does not match expected result | Fail | BUG-003 | Pending | Defect logged for investigation
TC-DASH-010 | Dashboard | Verify dashboard card UI displays correctly | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-001 | Product Management | Verify product list loads successfully | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-23 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-002 | Product Management | Verify product table columns display correctly | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-003 | Product Management | Verify Admin creates product with valid data | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-004 | Product Management | Verify product name required validation | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-005 | Product Management | Verify duplicate product name is rejected | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-006 | Product Management | Verify category required validation | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-007 | Product Management | Verify price required validation | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-008 | Product Management | Verify price equal 0 is rejected | Medium | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-009 | Product Management | Verify negative price is rejected | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-010 | Product Management | Verify initial quantity required validation | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-011 | Product Management | Verify initial quantity equal 0 is accepted | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-012 | Product Management | Verify negative initial quantity is rejected | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-013 | Product Management | Verify status required validation | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Cannot execute due to dependent issue/test data | Blocked |  | N/A | Blocked by environment or prerequisite data
TC-PROD-014 | Product Management | Verify Admin updates product name | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-015 | Product Management | Verify Admin updates product category | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result does not match expected result | Fail | BUG-004 | Pending | Defect logged for investigation
TC-PROD-016 | Product Management | Verify Admin updates product price | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-017 | Product Management | Verify Admin changes product status to Inactive | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-018 | Product Management | Verify Admin changes product status to Active | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-019 | Product Management | Verify product quantity cannot be edited directly | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-020 | Product Management | Verify Admin deletes product with quantity 0 and no history | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result does not match expected result | Fail | BUG-005 | Pending | Defect logged for investigation
TC-PROD-021 | Product Management | Verify product with quantity greater than 0 cannot be deleted | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-022 | Product Management | Verify product with stock-in history cannot be deleted | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-023 | Product Management | Verify product with stock-out history cannot be deleted | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-024 | Product Management | Verify Staff cannot see Add Product button | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-025 | Product Management | Verify Staff cannot edit product | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-026 | Product Management | Verify Staff cannot delete product | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-24 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-027 | Product Management | Verify product search by name | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result does not match expected result | Fail | BUG-006 | Pending | Defect logged for investigation
TC-PROD-028 | Product Management | Verify product filter by category | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-029 | Product Management | Verify product filter by status | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-PROD-030 | Product Management | Verify product pagination | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STIN-001 | Stock-In | Verify stock-in page loads successfully | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STIN-002 | Stock-In | Verify Admin creates stock-in with valid data | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STIN-003 | Stock-In | Verify Staff creates stock-in with valid data | High | Role-Based Access | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STIN-004 | Stock-In | Verify product required validation | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STIN-005 | Stock-In | Verify quantity required validation | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STIN-006 | Stock-In | Verify quantity equal 0 is rejected | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STIN-007 | Stock-In | Verify negative quantity is rejected | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STIN-008 | Stock-In | Verify inactive product cannot be selected | Medium | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STIN-009 | Stock-In | Verify stock-in increases product quantity | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STIN-010 | Stock-In | Verify stock-in transaction saved in history | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result does not match expected result | Fail | BUG-007 | Pending | Defect logged for investigation
TC-STIN-011 | Stock-In | Verify note can be optional | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STIN-012 | Stock-In | Verify selected product information displays correctly | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STIN-013 | Stock-In | Verify stock-in success message | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STIN-014 | Stock-In | Verify stock-in API error is displayed | Medium | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STOUT-001 | Stock-Out | Verify stock-out page loads successfully | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STOUT-002 | Stock-Out | Verify Admin creates stock-out with valid data | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STOUT-003 | Stock-Out | Verify Staff creates stock-out with valid data | High | Role-Based Access | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STOUT-004 | Stock-Out | Verify product required validation | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STOUT-005 | Stock-Out | Verify quantity required validation | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result does not match expected result | Fail | BUG-008 | Pending | Defect logged for investigation
TC-STOUT-006 | Stock-Out | Verify quantity equal 0 is rejected | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STOUT-007 | Stock-Out | Verify negative quantity is rejected | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-25 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STOUT-008 | Stock-Out | Verify quantity exceeding current stock is rejected | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Cannot execute due to dependent issue/test data | Blocked |  | N/A | Blocked by environment or prerequisite data
TC-STOUT-009 | Stock-Out | Verify inactive product cannot be selected | Medium | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STOUT-010 | Stock-Out | Verify stock-out decreases product quantity | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STOUT-011 | Stock-Out | Verify stock-out transaction saved in history | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STOUT-012 | Stock-Out | Verify reason can be optional | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STOUT-013 | Stock-Out | Verify selected product information displays correctly | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STOUT-014 | Stock-Out | Verify stock-out success message | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STOUT-015 | Stock-Out | Verify stock-out API error is displayed | Medium | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-STOUT-016 | Stock-Out | Verify product quantity never becomes negative | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-HIS-001 | Transaction History | Verify stock-in history list displays correctly | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-HIS-002 | Transaction History | Verify stock-out history list displays correctly | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result does not match expected result | Fail | BUG-009 | Pending | Defect logged for investigation
TC-HIS-003 | Transaction History | Verify stock-in history search by product name | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-HIS-004 | Transaction History | Verify stock-out history search by product name | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-HIS-005 | Transaction History | Verify stock-in history date range filter | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-HIS-006 | Transaction History | Verify stock-out history date range filter | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-HIS-007 | Transaction History | Verify stock-in detail modal | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-HIS-008 | Transaction History | Verify stock-out detail modal | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-HIS-009 | Transaction History | Verify history pagination | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-HIS-010 | Transaction History | Verify empty history state | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-REP-001 | Inventory Report | Verify inventory report page loads successfully | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-REP-002 | Inventory Report | Verify report displays product quantity | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-REP-003 | Inventory Report | Verify IN_STOCK status when quantity greater than 10 | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-REP-004 | Inventory Report | Verify LOW_STOCK status when quantity 1 to 10 | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result does not match expected result | Fail | BUG-010 | Pending | Defect logged for investigation
TC-REP-005 | Inventory Report | Verify OUT_OF_STOCK status when quantity 0 | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-REP-006 | Inventory Report | Verify filter by category | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-26 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-REP-007 | Inventory Report | Verify filter by stock status | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Cannot execute due to dependent issue/test data | Blocked |  | N/A | Blocked by environment or prerequisite data
TC-REP-008 | Inventory Report | Verify report quantity matches product list | High | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-REP-009 | Inventory Report | Verify report summary cards | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-REP-010 | Inventory Report | Verify report empty state | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-ROLE-001 | Role-Based Access | Verify Admin can access all main pages | High | Role-Based Access | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-ROLE-002 | Role-Based Access | Verify Staff can access allowed pages | High | Role-Based Access | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-ROLE-003 | Role-Based Access | Verify unauthenticated user cannot access dashboard | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-ROLE-004 | Role-Based Access | Verify unauthenticated user cannot access products | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-ROLE-005 | Role-Based Access | Verify Staff cannot access product create route | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-ROLE-006 | Role-Based Access | Verify Staff cannot access product edit route | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result does not match expected result | Fail | BUG-011 | Pending | Defect logged for investigation
TC-ROLE-007 | Role-Based Access | Verify Staff receives 403 for create product API | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-ROLE-008 | Role-Based Access | Verify Staff receives 403 for update product API | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-ROLE-009 | Role-Based Access | Verify Staff receives 403 for delete product API | High | Negative | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-ROLE-010 | Role-Based Access | Verify Admin can create stock-in | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-ROLE-011 | Role-Based Access | Verify Staff can create stock-in | High | Role-Based Access | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-ROLE-012 | Role-Based Access | Verify Admin can create stock-out | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result does not match expected result | Fail | BUG-012 | Pending | Defect logged for investigation
TC-ROLE-013 | Role-Based Access | Verify Staff can create stock-out | High | Role-Based Access | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-UI-001 | UI and Validation | Verify sidebar navigation items | Low | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-UI-002 | UI and Validation | Verify active menu highlight | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-UI-003 | UI and Validation | Verify success notification after create product | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-27 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-UI-004 | UI and Validation | Verify error notification after invalid action | High | Negative | System should behave according to requirement and business rules | admin/staff test data |  | Nguyen Phuc Tan |  | Not Run |  | N/A | Planned for next execution cycle
TC-UI-005 | UI and Validation | Verify delete confirmation modal | High | Functional | System should behave according to requirement and business rules | admin/staff test data |  | Nguyen Phuc Tan |  | Not Run |  | N/A | Planned for next execution cycle
TC-UI-006 | UI and Validation | Verify loading state while fetching data | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data |  | Nguyen Phuc Tan |  | Not Run |  | N/A | Planned for next execution cycle
TC-UI-007 | UI and Validation | Verify empty state when no data | Low | Functional | System should behave according to requirement and business rules | admin/staff test data |  | Nguyen Phuc Tan |  | Not Run |  | N/A | Planned for next execution cycle
TC-UI-008 | UI and Validation | Verify pagination UI | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data |  | Nguyen Phuc Tan |  | Not Run |  | N/A | Planned for next execution cycle
TC-UI-009 | UI and Validation | Verify form fields have clear labels | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-28 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-UI-010 | UI and Validation | Verify validation messages are readable | High | Validation | System should behave according to requirement and business rules | admin/staff test data | 2026-06-28 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-UI-011 | UI and Validation | Verify date format display | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-28 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A
TC-UI-012 | UI and Validation | Verify currency format display | Medium | Functional | System should behave according to requirement and business rules | admin/staff test data | 2026-06-28 | Nguyen Phuc Tan | Actual result matches expected result | Pass |  | N/A

## Defect Summary
Bug ID | Related Test Case ID | Module | Summary | Severity | Priority | Status | Detected Date | Retest Result | Notes
BUG-007 | TC-STIN-010 | Stock-In | stock-in transaction saved in history | High | High | Open | 2026-06-23 | Pending | Sample defect for portfolio test execution
BUG-010 | TC-REP-004 | Inventory Report | LOW_STOCK status when quantity 1 to 10 | High | High | Open | 2026-06-23 | Pending | Sample defect for portfolio test execution
BUG-001 | TC-AUTH-007 | Authentication | password required validation | Medium | Medium | Open | 2026-06-23 | Pending | Sample defect for portfolio test execution
BUG-004 | TC-PROD-015 | Product Management | Admin updates product category | Medium | Medium | Open | 2026-06-24 | Pending | Sample defect for portfolio test execution
BUG-008 | TC-STOUT-005 | Stock-Out | quantity required validation | High | High | Open | 2026-06-24 | Pending | Sample defect for portfolio test execution
BUG-005 | TC-PROD-020 | Product Management | Admin deletes product with quantity 0 and no history | Medium | Medium | Open | 2026-06-24 | Pending | Sample defect for portfolio test execution
BUG-011 | TC-ROLE-006 | Role-Based Access | Staff cannot access product edit route | High | High | Open | 2026-06-25 | Pending | Sample defect for portfolio test execution
BUG-006 | TC-PROD-027 | Product Management | product search by name | Low | Low | Open | 2026-06-25 | Pending | Sample defect for portfolio test execution
BUG-002 | TC-DASH-006 | Dashboard | low stock product count | Medium | Medium | Fixed | 2026-06-25 | Pass | Sample defect for portfolio test execution
BUG-012 | TC-ROLE-012 | Role-Based Access | Admin can create stock-out | High | High | Fixed | 2026-06-26 | Pass | Sample defect for portfolio test execution
BUG-009 | TC-HIS-002 | Transaction History | stock-out history list displays correctly | Medium | Medium | Fixed | 2026-06-26 | Pass | Sample defect for portfolio test execution
BUG-003 | TC-DASH-009 | Dashboard | dashboard handles API error | Low | Low | Fixed | 2026-06-26 | Pass | Sample defect for portfolio test execution

## Lists
Priority | Status | Retest Status | Severity | Module | Test Type
High | Pass | N/A | Critical | Authentication | Functional
Medium | Fail | Pending | High | Dashboard | Negative
Low | Blocked | Pass | Medium | Product Management | Validation
| Not Run | Fail | Low | Stock-In | Business Rule
|  | Blocked |  | Stock-Out | Role-Based Access
|  |  |  | Transaction History | Security
|  |  |  | Inventory Report | UI
|  |  |  | Role-Based Access | Data Integrity
|  |  |  | UI and Validation | Regression