## Summary
StockFlow Bug Report Summary
Metric | Formula / Value
Total Bugs | 12
Critical Bugs | 2
High Severity Bugs | 6
Open Bugs | 5
Closed Bugs | 7
Pass Retest | 7
Severity | Count
Critical | 2
High | 6
Medium | 3
Low | 1
Status | Count
New | 0
Open | 5
In Progress | 0
Fixed | 0
Closed | 7
Reopened | 0

## Sample Bug Reports
Bug ID | Module | Summary | Description | Steps to Reproduce | Test Data | Expected Result | Actual Result | Severity | Priority | Status | Environment | Screenshot/Attachment | Assigned To | Reported Date | Fixed Date | Retest Result | Related Test Case ID | Notes
BUG-001 | Stock-Out | Stock-out quantity greater than current stock is accepted | The system should reject stock-out quantity that exceeds current inventory, but the transaction is still submitted in some cases. | 1. Login as admin 2. Open Stock-Out page 3. Select product with quantity 3 4. Enter stock-out quantity 5 5. Click Submit | Product: Mouse Logitech, Current quantity: 3, Stock-out quantity: 5 | System shows error message: Stock-out quantity cannot exceed current inventory quantity. Product quantity remains unchanged. | Stock-out transaction is submitted and product quantity is reduced incorrectly. | Critical | High | Closed | Windows 11, Chrome, FE localhost:3000, BE localhost:8080 | screenshot_bug_001.png | Developer | 2026-06-23 | 2026-06-23 | Pass | TC-STOUT-007 | Important data integrity bug.
BUG-002 | Product Management | Staff can access product create page directly by URL | Staff user should not access Admin-only product create route directly. | 1. Login as staff 2. Enter URL /products/create directly 3. Observe page behavior | User: staff / 123456 | System redirects Staff to dashboard or shows access denied. | Product create page is displayed to Staff. | High | High | Closed | Windows 11, Chrome | screenshot_bug_002.png | Developer | 2026-06-23 | 2026-06-23 | Pass | TC-ROLE-007 | Role-based access issue.
BUG-003 | Product Management | Duplicate product name validation message is unclear | When Admin creates a product with an existing name, the error message does not clearly explain the issue. | 1. Login as admin 2. Create product named Laptop Dell Inspiron 3. Create another product with the same name 4. Click Submit | Product name: Laptop Dell Inspiron | System displays clear message: Product name already exists. | System displays generic system error. | Medium | Medium | Open | Windows 11, Chrome | screenshot_bug_003.png | Developer | 2026-06-23 |  | Not Retested | TC-PROD-006 | Validation message should be user-friendly.
BUG-004 | Product Management | Delete confirmation modal is not displayed before deleting product | The system should ask for confirmation before deleting a product. | 1. Login as admin 2. Open Product List 3. Click Delete button on a deletable product | Product quantity: 0, no transaction history | Confirmation modal is displayed before delete action. | Product is deleted immediately without confirmation. | Medium | Medium | Closed | Windows 11, Chrome | screenshot_bug_004.png | Developer | 2026-06-23 | 2026-06-23 | Pass | TC-UI-005 | UI safety issue.
BUG-005 | Stock-In | Stock-in allows quantity 0 | Stock-in quantity must be greater than 0, but the form allows quantity 0 to be submitted. | 1. Login as admin 2. Open Stock-In page 3. Select an active product 4. Enter quantity 0 5. Submit | Quantity: 0 | System rejects the request and shows quantity must be greater than 0. | System submits the stock-in transaction. | High | High | Closed | Windows 11, Chrome | screenshot_bug_005.png | Developer | 2026-06-23 | 2026-06-23 | Pass | TC-STIN-006 | Boundary validation bug.
BUG-006 | Stock-Out | Stock-out page auto-clamps quantity instead of showing validation error | When user enters stock-out quantity greater than current stock, the input is automatically changed to max stock instead of displaying validation error. | 1. Login as admin 2. Open Stock-Out page 3. Select product with quantity 3 4. Enter quantity 5 5. Observe input value | Current quantity: 3, Entered quantity: 5 | System keeps entered value and shows validation error. | Input is automatically changed from 5 to 3. | Medium | Medium | Closed | Windows 11, Chrome | screenshot_bug_006.png | Developer | 2026-06-23 | 2026-06-23 | Pass | TC-STOUT-007 | Previously discussed frontend issue.
BUG-007 | Transaction History | Sidebar highlights Stock-Out menu when viewing Stock-In History | The active sidebar menu is incorrect when user opens Stock-In History. | 1. Login as admin 2. Click Stock-In History 3. Observe sidebar active menu | Route: /stock-in/history | Stock-In History menu is highlighted. | Stock-Out menu is highlighted. | Low | Medium | Closed | Windows 11, Chrome | screenshot_bug_007.png | Developer | 2026-06-23 | 2026-06-23 | Pass | TC-UI-002 | Navigation UI bug.
BUG-008 | Inventory Report | LOW_STOCK status is not displayed correctly for quantity 10 | Quantity 10 should be classified as LOW_STOCK, but report displays IN_STOCK. | 1. Login as admin 2. Create product with quantity 10 3. Open Inventory Report 4. Check stock status | Quantity: 10 | Stock status is LOW_STOCK. | Stock status is IN_STOCK. | High | High | Open | Windows 11, Chrome | screenshot_bug_008.png | Developer | 2026-06-23 |  | Not Retested | TC-REP-004 | Boundary value bug.
BUG-009 | Authentication | Protected page can be accessed after logout using browser back button | After logout, user should not be able to view protected data using browser back button. | 1. Login as admin 2. Open Dashboard 3. Logout 4. Click browser Back button | User: admin / 123456 | User stays on login page or protected page redirects to login. | Dashboard content is displayed again. | High | High | Open | Windows 11, Chrome | screenshot_bug_009.png | Developer | 2026-06-23 |  | Not Retested | TC-AUTH-008 | Authentication/session handling issue.
BUG-010 | Dashboard | Dashboard total stock quantity does not update after stock-in | Dashboard should reflect updated stock quantity after stock-in transaction. | 1. Login as admin 2. Note dashboard total stock quantity 3. Create stock-in transaction quantity 5 4. Return to dashboard 5. Click Refresh | Stock-in quantity: 5 | Total stock quantity increases by 5. | Total stock quantity remains unchanged. | High | Medium | Closed | Windows 11, Chrome | screenshot_bug_010.png | Developer | 2026-06-23 | 2026-06-23 | Pass | TC-DASH-004 | Data sync issue.
BUG-011 | Product Management | Product price accepts negative value through API | Frontend validation blocks negative price, but API still accepts negative value. | 1. Login as admin 2. Send POST /api/products using Postman 3. Set price = -1000 4. Observe response | price: -1000 | API rejects request with validation error. | API creates product successfully. | High | High | Open | Postman, BE localhost:8080 | postman_bug_011.png | Developer | 2026-06-23 |  | Not Retested | TC-PROD-008 | Backend validation issue.
BUG-012 | Database | Stock-out failed transaction still creates transaction record | When stock-out request fails due to insufficient inventory, no transaction record should be inserted. | 1. Prepare product with quantity 3 2. Submit stock-out quantity 5 via API 3. Check stock_out_transactions table | Product quantity: 3, Stock-out quantity: 5 | Request is rejected and no stock-out transaction is created. | Request is rejected but a stock-out transaction record is still inserted. | Critical | High | Open | MySQL, Postman | db_bug_012.png | Developer | 2026-06-23 |  | Not Retested | TC-STOUT-007 | Database integrity bug.

## Bug Report Template
Field | Description | Example
Bug ID | Unique bug identifier | BUG-001
Module | Feature/module where bug occurs | Stock-Out
Summary | Short bug title | Stock-out quantity greater than current stock is accepted
Description | Detailed description of the problem | The system allows stock-out transaction with invalid quantity.
Steps to Reproduce | Clear steps to reproduce the bug | 1. Login 2. Open Stock-Out 3. Enter invalid quantity
Test Data | Data used during testing | Product quantity: 3, Stock-out quantity: 5
Expected Result | Expected behavior based on requirement | System rejects the transaction.
Actual Result | Actual behavior observed | Transaction is submitted.
Severity | Impact level | Critical / High / Medium / Low
Priority | Fix urgency | High / Medium / Low
Status | Bug lifecycle status | New / Open / In Progress / Fixed / Closed / Reopened
Environment | Testing environment | Windows 11, Chrome, localhost
Screenshot/Attachment | Evidence file name or link | screenshot_bug_001.png
Assigned To | Person responsible for fix | Developer
Reported Date | Date when bug is reported | 2026-06-23
Fixed Date | Date when bug is fixed | 2026-06-24
Retest Result | Retest status after fix | Pass / Fail / Not Retested
Related Test Case ID | Related manual/API/DB test case | TC-STOUT-007
Notes | Additional notes | Important business rule bug

## Lists
Severity | Priority | Status | Module | Retest Result
Critical | High | New | Authentication | Pass
High | Medium | Open | Dashboard | Fail
Medium | Low | In Progress | Product Management | Not Retested
Low |  | Fixed | Stock-In | Blocked
|  | Closed | Stock-Out
|  | Reopened | Transaction History
|  | Rejected | Inventory Report
Role-Based Access
API Testing
Database
UI